## Project 1
Project # |  |  |  | Project Start |  |  | Project End
Location
Project Scope
Customer Accepted | Yes |  |  | Completion | 62.5%
SNAPSHOT - PROJECTIONS | [5 empty] | SNAPSHOT - ACTUALS
Bid Total | 30950 |  |  |  |  | Net Revenue Actuals |  | 5327
Net Profit | 12% |  |  |  |  | Net Profit |  | 17.21%
Fixed Costs Applied | 1175 |  |  |  |  | Labor Cost Variance |  | 360
[6 empty] | Material Variance |  | -139
Phase | Bid | Projected Materials Costs | Projected Labor Costs | Total Controllable Cost | Indirect & Overhead | Projected Net Revenue | Status | Actual Material Costs | Actual Labor Cost | Actual Net Revenue | Variance
Prep 1 (Permits) | 700 | 500 | 18 | 518 | 100 | 82 | Completed | 500 | 18 | 82 | 0
Prep 1 (City Planning) | 1500 | 800 | 300 | 1100 | 300 | 100 | Completed | 835 | 300 | 65 | -35
Prep 2 (Excavate) | 4250 | 1215 | 1872 | 3087 | 75 | 1088 | Completed | 1000 | 2808 | 367 | -721
Prep 4 (Concrete) | 6250 | 4950 | 368 | 5318 | 100 | 832 | Completed | 5380 | 368 | 402 | -430
Build 1 (Frame) | 8800 | 1675 | 6144 | 7819 | 100 | 881 | Completed | 1625 | 3840 | 3235 | 2354
Build 2 (Decking) | 7000 | 1300 | 4992 | 6292 | 200 | 508 | Not Started | 1400 | 4608 | 792 | 284
Build 3 (Railings) | 1650 | 725 | 800 | 1525 | 100 | 25 | Not Started | 664 | 800 | 86 | 61
Finish 1 | 800 | 250 | 152 | 402 | 200 | 198 | Not Started | 150 | 152 | 298 | 100
0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
Material Tracker | [5 empty] | Labor Tracker
Phase | Material | Estimate Cost | Actual | Variance |  | Phase | Contractor | Rate | Estimated Hours | Actual Hours | Variance
Prep 1 (Permits) |  | 500 | 500 | 0 |  | Prep 1 (City Planning) | Chris | 32 | 3 | 3 | 0
Prep 1 (City Planning) |  | 800 | 835 | -35 |  | Prep 1 (City Planning) | Jason | 18 | 3 | 3 | 0
Prep 2 (Excavate) | Backhoe | 1215 | 1000 | 215 |  | Prep 2 (Excavate) | John | 27 | 8 | 12 | -108
Prep 4 (Concrete) | Concrete Footings | 4950 | 5380 | -430 |  | Prep 2 (Excavate) | Kevin | 19 | 8 | 12 | -76
Build 1 (Frame) | Wood 12x12 treated frame | 1000 | 1025 | -25 |  | Prep 2 (Excavate) | Chris | 32 | 8 | 12 | -128
Build 1 (Frame) | Wood 6x6 treated frame | 675 | 600 | 75 |  | Prep 1 (Permits) | Jason | 18 | 1 | 1 | 0
Build 2 (Decking) | Wood 6x2 treated decking | 1300 | 1400 | -100 |  | Prep 4 (Concrete) | John | 27 | 4 | 4 | 0
Build 3 (Railings) | Wood 2x4 treated railings | 500 | 475 | 25 |  | Prep 4 (Concrete) | Kevin | 19 | 4 | 4 | 0
Build 3 (Railings) | Wood balisters railings | 225 | 189 | 36 |  | Build 1 (Frame) | Chris | 32 | 16 | 10 | 192
Finish 1 | Stain | 250 | 150 | 100 |  | Build 1 (Frame) | Jason | 18 | 16 | 10 | 108
|  |  |  | 0 |  | Build 1 (Frame) | John | 27 | 16 | 10 | 162
|  |  |  | 0 |  | Build 1 (Frame) | Kevin | 19 | 16 | 10 | 114
|  |  |  | 0 |  | Build 2 (Decking) | Chris | 32 | 13 | 12 | 32
|  |  |  | 0 |  | Build 2 (Decking) | Jason | 18 | 13 | 12 | 18
|  |  |  | 0 |  | Build 2 (Decking) | John | 27 | 13 | 12 | 27
|  |  |  | 0 |  | Build 2 (Decking) | Kevin | 19 | 13 | 12 | 19
|  |  |  | 0 |  | Build 3 (Railings) | Chris | 32 | 8 | 8 | 0
|  |  |  | 0 |  | Build 3 (Railings) | Jason | 18 | 8 | 8 | 0
|  |  |  | 0 |  | Finish 1 | Kevin | 19 | 8 | 8 | 0
|  |  |  | 0 | [6 empty] | 0
|  |  |  | 0 | [6 empty] | 0
|  |  |  | 0 | [6 empty] | 0
|  |  |  | 0 | [6 empty] | 0
|  |  |  | 0 | [6 empty] | 0
|  |  |  | 0 | [6 empty] | 0

## Directions
All Sheets in this workbook are unprotected
Make a copy of original before changing any formula driven cells
To start a new Project Bid
Left Click on Project tab and select move or copy
Select "Create a Copy" and then "Ok"
Rename new tab
New Project
Input all relevant data in the unhighted cells
All Grey highlighted cells are formula driven and will auto populate with new data